## Comments
Project: |  | C9727 - I-405, Brickyard to SR 527 Improvement Project |  |  |  |  | CODES
Document Name: |  | BY-CRE-00552_009727_SUB_17.01_Segment 3 Preliminary Structures 103E-W |  |  |  |  | A = Accept Comment - Correct, Add to, or Clarify document
Submittal Date: |  | 2024-05-01 |  | Formal Design Review |  |  | D = Dismiss Comment - no change needed on document
Due Date: |  | 2024-05-22 | COB | Form RCSR (Review Comment Summary and Resolution) |  |  | C = Clarify / Discuss and resolve before next design phase
Reviewer: |  | Terry Bondy (TB), Dan Scheil - AWWD (DS), Minako McWreath (MM) |  |  |  |  | R = Resolve comment in the next submittal phase
Document Lead: | [6 empty] | T = Transfer to a different submittal
COMMENT (WSDOT, City, Checker) |  |  |  | RESPONSE TO COMMENT (Skanska, Originator of Document) |  |  | RESPONSE TO RESPONSE (WSDOT, City, Checker) |  | Skanska CLOSE
No. | Report or Sheet No. | Comment By | Comment | Disposition Code | Response By | ACTION TAKEN / Remarks | WSDOT Disposition Code | Comments / Action Items | Final Disposition Code
1 | All | TB | Please be sure the at information required in the Preliminary Plan Check list is provided (2.13.17.1.1.) Grading contours missing, structure type, barrier wall face treatments (App L2), location of temporary barrier, to name a few.
2 | BF06 | TB | Add a locations of temporary barrier to the Typical Section near the edge of the bridge where the existing barrier is to be removed. (2.13.7.1.1)
3 | BF06 | TB | The typical section shows a 10'-0" lane on the far right side of the bridge, but no shoulder. Is this correct? Sheet BF18 shows this as a 10'-0" shoulder.
4 | BF18; Calcs page 15 of 313 | TB | Sheet BF18 shows 0.25 ft of HMA overlay, while Calcs page 15 of 313 shows 1.5 inches of HMA overlay. Please confirm which is accurate and revise as necessary. Update values to meet minimum deck thickness and deck protection system.
5 | BB14; Calcs page 49 of 313 | TB | Sheet BG14 shows 0.25 ft of HMA overlay, while Calcs page 49 of 313 shows 1.5 inches of HMA overlay. Please confirm which is accurate and revise as necessary. Update values to meet minimum deck thickness and deck protection system.
6 | BF18 | TB | 6.5" deck thickness does not meet minimum deck thickness. Per BDM 15.5.5A, The minimum bridge deck thickness shall be 5″ for slab and deck bulb-tee prestressed concrete girder superstructures, 7.5″ for other concrete superstructures, 8.0″ for steel girder superstructures, and 8.5″ (including 3.5″ stay-in-place deck panel and 5″ CIP concrete deck) for superstructures with SIP deck panels. This minimum thickness may be reduced by 0.5″ for bridges with Deck Protection Systems 2, 3 and 5. For bridge deck overhangs that support traffic barriers, the minimum thickness shall be 8”.
7 | BF18 | TB | Call out HMA with waterproofing membrane. The deck protection system is required to meet 5.7.4B. Suggest early evaluation of existing deck reinforcing and how it is to align with new deck reinforcing to meet deck protection system. 5.7.4.B.1
8 | BF18 | TB | Sewer line is called out. Is it a storm sewer or sewer? Call out ductile iron and size.
9 | BF06 | TB | Please explain why a closure pour in the cap and pier wall is not shown between the widened and existing portions of the bridge. What bearing pressures and settlements are anticipated for the new spread footings? In addition to bridge superstructure loading, the backfill of the deep excavation will cause settlements that further increase the differential between old and new portions. Per BDM 15.2.10, Differential settlement between the new and existing structures shall be taken into account...If the widening requires additional girders or substructure, a closure strip shall be provided. Per BDM 15.4.3B3, The designer shall evaluate the potential for differential settlement between the existing structure and widening structure. Additional geotechnical measures may be required to limit differential settlements to tolerable levels for both static and seismic conditions. The bridge designer shall evaluate, design, and detail all elements of new and existing portions of the widened structure for the differential settlement warranted by the Geotechnical Engineer. Angular distortions between adjacent foundations shall not exceed 0.008 (RAD) in simple spans and 0.004 (RAD) in continuous spans.
10 | BF05 | TB | Show and callout bridge security fencing, which is required per 2.13.4.1.13
11 | BF05 | TB | Callout concrete slope protection, which is required per 2.13.4.1.8.
12 | BF05 | TB | Left side of elevation view shows final grade leveling out at the abutment. The horizontal bench shown shall be omitted. Per BDM 15.2.11B, Horizontal graded landform shelves at the abutment face beneath superstructures shall be omitted and leader for existing grade pointing towards final.
13 | BF04 | TB | Storm inlets shown are too close to the ends of the bridge. Per BDM 15.10.6, Bridge runoff at the abutments shall be carried off and collected at least 10 feet beyond the bridge approach slab.
14 | BF06 | TB | Will bolsters or seat length extensions be provided (intermediate piers or abutments)? (2.13.4.1.2)
15 | BF06 | TB | Preliminary plans do not capture scope of work. Will additional girderstops or girderstop extension be provided, such as at the abutments? Per 2.13.4.1.2, Provide full width transverse girder stops between each girder at each girder support. As build plans to do not show girder stops are full width and between each girder.
16 | BF06 | TB | Preliminary plans do not capture scope of work. How is strengthening of the existing spread footings be provided? As builts show only a bottom mat of rebar in the footings. Per 2.13.4.1.2, Provide foundation strengthening below top of existing footings to resist seismic inertial demands. Existing shallow spread footings at the intermediate piers shall be made continuous to form a catenary or deep beam across the pier. Calculations contain illustrations of top reinforcing added and thickening of the spread footing, but submitted plans do not.
17 | BF35 | TB | Construction work zone is shown at or beyond culvert outlet and inside OHW. How has the extents of the work zone been vetted with environmental permits and methods to support and protect the pipe been establish?
18 | BF05 | TB | What are the plans to address the blunt end hazard of the noise wall on the barrier?
19 | BG02 | TB | Light poles are shown being added to the bridge approximately mid span. Per 2.13.4.8, Overhead lighting, sign bridges, cantilever sign structures, signal bridges, and overhead cantilever traffic signals mounted on bridges shall be attached either to the bridge substructure elements (e.g., crossbeam extensions) or to the bridge superstructure at piers locations. Suggest moving the light pole off the bridge if possible or locating at pier. Please request deviation if needed. Vibration and frequency will need to be evaluated. Given the barrier is existing, connecting the light pole will need to meet App L2 and BDM requirements for attachment of utilities. Does existing barrier have capacity for attachment? How will power be routed?
20 | BG sheets | TB | Scope of retrofit work not captured in plans. See comments above for BF sheets and 2.13.4.1.14
21 | BG sheets | TB | Some of the above comments apply to BF sheets.
22 | General | DS | There was no notes made for any conflicts with the exiting water and sewer main with 228th St SE. Need to provide method of construction when working near these mains
23 | BF06, BG14 | MM | Infill pier walls shall receive ashlar finish with Mt. St. Helens pigmented sealer.
24
25
26
27
28
29
30
31
32
33
34
35
36