## Comments
| Project: |  | C9727 - I-405, Brickyard to SR 527 Improvement Project |  |  |  |  | CODES
| Document Name: |  | BY-CRE-00552_009727_SUB_17.01_Segment 3 Preliminary Structures 103E-W |  |  |  |  | A = Accept Comment - Correct, Add to, or Clarify document
| Submittal Date: |  | 2024-05-01 |  | Formal Design Review |  |  | D = Dismiss Comment - no change needed on document
| Due Date: |  | 2024-05-22 | COB | Form RCSR (Review Comment Summary and Resolution) |  |  | C = Clarify / Discuss and resolve before next design phase
| Reviewer: |  | Terry Bondy (TB), Dan Scheil - AWWD (DS), Minako McWreath (MM) |  |  |  |  | R = Resolve comment in the next submittal phase
| Document Lead: | [6 empty] | T = Transfer to a different submittal
| COMMENT (WSDOT, City, Checker) |  |  |  | RESPONSE TO COMMENT (Skanska, Originator of Document) |  |  | RESPONSE TO RESPONSE (WSDOT, City, Checker) |  | Skanska CLOSE
| No. | Report or Sheet No. | Comment By | Comment | Disposition Code | Response By | ACTION TAKEN / Remarks | WSDOT Disposition Code | Comments / Action Items | Final Disposition Code
| 1 | All | TB | Please be sure the at information required in the Preliminary Plan Check list is provided (2.13.17.1.1.) Grading contours missing, structure type, barrier wall face treatments (App L2), location of temporary barrier, to name a few. | A | ST | Noted. Will check and add grading contours, add PC Girder (W58G) (discussion with WSDOT is needed for W58G as it will reduce the vertical clearance). Will add architectural treatment and check against Preliminary Plan Check list | A | Comment addressed. WSDOT understands that this information will be included in the Final submittal.
| 2 | BF06 | TB | Add a locations of temporary barrier to the Typical Section near the edge of the bridge where the existing barrier is to be removed. (2.13.7.1.1) | A | ST | Noted. In the final submittal, will add a temporary barrier in the construction staging drawing. | A | Comment addressed.
| 3 | BF06 | TB | The typical section shows a 10'-0" lane on the far right side of the bridge, but no shoulder. Is this correct? Sheet BF18 shows this as a 10'-0" shoulder. | A | ST | Will revise "lane" to "shoulder". | A | Comment addressed.
| 4 | BF18; Calcs page 15 of 313 | TB | Sheet BF18 shows 0.25 ft of HMA overlay, while Calcs page 15 of 313 shows 1.5 inches of HMA overlay. Please confirm which is accurate and revise as necessary. Update values to meet minimum deck thickness and deck protection system. | A | ST | New HMA is 0.25'. Will revise calculations. | A | Comment addressed.
| 5 | BB14; Calcs page 49 of 313 | TB | Sheet BG14 shows 0.25 ft of HMA overlay, while Calcs page 49 of 313 shows 1.5 inches of HMA overlay. Please confirm which is accurate and revise as necessary. Update values to meet minimum deck thickness and deck protection system. | A | ST | New HMA is 0.25'. Will revise calculations. | A | Comment addressed.
| 6 | BF18 | TB | 6.5" deck thickness does not meet minimum deck thickness. Per BDM 15.5.5A, The minimum bridge deck thickness shall be 5″ for slab and deck bulb-tee prestressed concrete girder superstructures, 7.5″ for other concrete superstructures, 8.0″ for steel girder superstructures, and 8.5″ (including 3.5″ stay-in-place deck panel and 5″ CIP concrete deck) for superstructures with SIP deck panels. This minimum thickness may be reduced by 0.5″ for bridges with Deck Protection Systems 2, 3 and 5. For bridge deck overhangs that support traffic barriers, the minimum thickness shall be 8”. | A | ST | will revise to 7.5" for deck thickness and 8" at edge of deck overhang | A | Comment addressed.
| 7 | BF18 | TB | Call out HMA with waterproofing membrane. The deck protection system is required to meet 5.7.4B. Suggest early evaluation of existing deck reinforcing and how it is to align with new deck reinforcing to meet deck protection system. 5.7.4.B.1 | A | ST | will revise to "New 0.25' HMA overlay with waterproofing membrane (TYP)". The actual concrete cover of the existing deck will be known when the existing deck is removed, but will provide details to ensure the widening portion of the deck meets Type 1 deck protection. | A | Comment addressed.
#8# | 8 | BF18 | TB | Sewer line is called out. Is it a storm sewer or sewer? Call out ductile iron and size. |  | ST | The new storm drain pipe on the NB 405 bridge extension will be an 18” ductile iron pipe. Please note that final conveyance calcs have not yet been performed for this pipe run so this is subject to change. Also, there will be a new 12” ductile iron pipe hung from the existing SB 405 228th bridge. Please note that final conveyance calcs have not been performed for this pipe run so this is subject to change. The existing 18” pipe on the opposite side for the SB 405 228th bridge will remain. New bridge inlets will be needed on both sides of the existing SB 405 228th bridge due to narrower shoulders being proposed and the need to keep flow spread within the narrow shoulders. The bridge drain locations have not been determined yet. | D | Comment addressed. WSDOT understands that this information will be included in the Final submittal.
| 9 | BF06 | TB | Please explain why a closure pour in the cap and pier wall is not shown between the widened and existing portions of the bridge. What bearing pressures and settlements are anticipated for the new spread footings? In addition to bridge superstructure loading, the backfill of the deep excavation will cause settlements that further increase the differential between old and new portions. Per BDM 15.2.10, Differential settlement between the new and existing structures shall be taken into account...If the widening requires additional girders or substructure, a closure strip shall be provided. Per BDM 15.4.3B3, The designer shall evaluate the potential for differential settlement between the existing structure and widening structure. Additional geotechnical measures may be required to limit differential settlements to tolerable levels for both static and seismic conditions. The bridge designer shall evaluate, design, and detail all elements of new and existing portions of the widened structure for the differential settlement warranted by the Geotechnical Engineer. Angular distortions between adjacent foundations shall not exceed 0.008 (RAD) in simple spans and 0.004 (RAD) in continuous spans. | C | ST | A closure strip will be provided in the deck slab. For the substructure, the new widening portion will be separate from the existing structure using a 1/2" pre-molded joint filler to control and minimize differential settlement. | A | Comment addressed. Please show closure pour in FIN submittal.
| 10 | BF05 | TB | Show and callout bridge security fencing, which is required per 2.13.4.1.13 | C | ST | Per 2.13.4.1.13, security fencing is required for widened bridges with a clear height of 10 feet or less from the ground line to the girder seat. The security fencing may not be required for this bridge as the height is likely to exceed 10 feet. | D | Comment addressed. WSDOT understands that the decision to include or not include bridge security fencing will be finalized prior to the Final submittal.
| 11 | BF05 | TB | Callout concrete slope protection, which is required per 2.13.4.1.8. | A | ST | will show and call out "slope protection at widened portion only. | A | Comment addressed.
| 12 | BF05 | TB | Left side of elevation view shows final grade leveling out at the abutment. The horizontal bench shown shall be omitted. Per BDM 15.2.11B, Horizontal graded landform shelves at the abutment face beneath superstructures shall be omitted and leader for existing grade pointing towards final. | A | ST | will revise and omit berm. | A | Comment addressed.
| 13 | BF04 | TB | Storm inlets shown are too close to the ends of the bridge. Per BDM 15.10.6, Bridge runoff at the abutments shall be carried off and collected at least 10 feet beyond the bridge approach slab. |  | ST | We will adjust the storm drain inlets so that are no closer than 10’ to the approach slab. | A | Comment addressed.
| 14 | BF06 | TB | Will bolsters or seat length extensions be provided (intermediate piers or abutments)? (2.13.4.1.2) | C | ST | Seat extensions will be provided in the abutments, but not in the intermediate piers where the superstructure is pin-connected to the cross beams. | D | Comment addressed.
| 15 | BF06 | TB | Preliminary plans do not capture scope of work. Will additional girderstops or girderstop extension be provided, such as at the abutments? Per 2.13.4.1.2, Provide full width transverse girder stops between each girder at each girder support. As build plans to do not show girder stops are full width and between each girder. | A | ST | will provide full width girder stops at abutments in final design submittal. | A | Comment addressed.
| 16 | BF06 | TB | Preliminary plans do not capture scope of work. How is strengthening of the existing spread footings be provided? As builts show only a bottom mat of rebar in the footings. Per 2.13.4.1.2, Provide foundation strengthening below top of existing footings to resist seismic inertial demands. Existing shallow spread footings at the intermediate piers shall be made continuous to form a catenary or deep beam across the pier. Calculations contain illustrations of top reinforcing added and thickening of the spread footing, but submitted plans do not. | A | ST | Will provide a footing overlay retrofit with drilled and bonded dowel connections. The new footing will be integral with the existing footing through these dowels.. The combined new and existing footing will be checked for anticipated loadings. | A | Comment addressed.
| 17 | BF35 | TB | Construction work zone is shown at or beyond culvert outlet and inside OHW. How has the extents of the work zone been vetted with environmental permits and methods to support and protect the pipe been establish? | A/R | ST | The proposed new footing, as shown in the image, will be outside the culvert OHW. We will revise the construction zone to ensure it is also outside the culvert OHW | A | Comment addressed.
| 18 | BF05 | TB | What are the plans to address the blunt end hazard of the noise wall on the barrier? | A | ST | For final design, the noise wall is positioned on top of retaining wall 26.34 along the length the approach slab, and has been positioned outside the zone of intrusion to avoid a blunt end collision. The noise wall tapers in beyond the approach slab to align immediately behind the barrier but still avoids the blunt end impact | A | Comment addressed.
| 19 | BG02 | TB | Light poles are shown being added to the bridge approximately mid span. Per 2.13.4.8, Overhead lighting, sign bridges, cantilever sign structures, signal bridges, and overhead cantilever traffic signals mounted on bridges shall be attached either to the bridge substructure elements (e.g., crossbeam extensions) or to the bridge superstructure at piers locations. Suggest moving the light pole off the bridge if possible or locating at pier. Please request deviation if needed. Vibration and frequency will need to be evaluated. Given the barrier is existing, connecting the light pole will need to meet App L2 and BDM requirements for attachment of utilities. Does existing barrier have capacity for attachment? How will power be routed? | A | ST | will work with civil/sign team to either move the pole out of bridge or locate it in pier location | A | Comment addressed. WSDOT understands that the pole location will be finalized in the Final submittal.
| 20 | BG sheets | TB | Scope of retrofit work not captured in plans. See comments above for BF sheets and 2.13.4.1.14. | A | ST | Noted | A | Comment addressed.
| 21 | BG sheets | TB | Some of the above comments apply to BF sheets. | A | ST | Noted | A | Comment addressed. WSDOT understands that the revisions described in the comment responses above will be made for both BF and BG sheets as applicable.
| 22 | General | DS | There was no notes made for any conflicts with the exiting water and sewer main with 228th St SE. Need to provide method of construction when working near these mains | A/R | ST | Will add notes for potential utility conflicts including existing water and sewer main. Skanska will provide support measures to protect existing pipes.
| 23 | BF06, BG14 | MM | Infill pier walls shall receive ashlar finish with Mt. St. Helens pigmented sealer. | A | ST | Will call out architectural treatment
24
25
26
27
28
29
30
31
32
33
34
35
36